## Tabelle1
Sprint Events Duration Calculator
Sprint Duration (days) | 20
Hours / Day | 6
Developer 1 – available days | 20 | 120
Developer 2 | 20 | 120
Developer 3 | 20 | 120
Developer 4 | 20 | 120
Developer 5 | 20 | 120
Developer 6 | 20 | 120
Developer 7 | 20 | 120
Developer 8 | 20 | 120
Developer 9 | 20 | 120
| Total | 1080
Daily Scrum | 15 | Minutes
Sprint Planning | 8 | Hours
Sprint Retrospective | 3 | Hours
Sprint Review | 4 | Hours
Product Backlog Refinement | 108 | Hours
Total available working hours | 942 | 87.2222
Note on B3: Remove holidays, sick-leaves, etc.
Note on B4: Take 6 hours a day as standard, later you can adapt the value as needed.
Note on B7: Remove holidays, vacation, sick-leave, etc.
Note on B19: Fixed value
Note on B23: Not mandatory but no longer than this
Note on C24: Percentage of productive hours (programming)